## Лист1
Task | System Part | Task Type | Begin Date | Finish Date | Responsible
Team meeting | All | Meeting | 18.04.2017 |  | Guzel Mussilova
Meeting with Supervisor | All | Meeting | 19.04.2017 |  | Gabriel Campero
MS-I. Kick-Off | All | Presentation | 23.04.2017 | 01.05.2017 | Pavlo Shevchenko, Ali Hashaam
Team meeting | All | Meeting | 24.04.2017 |  | Guzel Mussilova
Meeting with Supervisor | All | Meeting | 26.04.2017 |  | Gabriel Campero
Team meeting | All | Meeting | 01.05.2017 |  | Guzel Mussilova
MS-I. Kick-Off | All | Presentation | 03.05.2017 |  | Pavlo Shevchenko, Ali Hashaam
Meeting with Supervisor | All | Meeting | 03.05.2017 |  | Gabriel Campero
DropWizard | Back-end | Research | 03.05.2017 | 10.05.2017 | Pavlo Shevchenko
Jupyter Notebook | Front-end | Research | 03.05.2017 | 10.05.2017 | Ali Hashaam
AQP Synopses | All | Research | 03.05.2017 | 11.05.2017 | Guzel Mussilova, Ali Raza
Load data from CSV | Front-end | Implementation | 04.05.2017 | 10.05.2017 | Ali Hashaam
Team meeting | All | Meeting | 08.05.2017 |  | Guzel Mussilova
Meeting with Supervisor | All | Meeting | 10.05.2017 |  | Gabriel Campero
Classes (Lineitem, Order) | Back-end | Implementation | 10.05.2017 | 15.05.2017 | Pavlo Shevchenko
Resource class(Primary Log) | Back-end | Implementation | 10.05.2017 | 15.05.2017 | Pavlo Shevchenko
Data Import | Back-end | Implementation | 10.05.2017 | 15.05.2017 | Pavlo Shevchenko
StorageView POJO | Back-end | Implementation | 10.05.2017 | 15.05.2017 | Pavlo Shevchenko
StorageView Manager | Back-end | Implementation | 10.05.2017 | 15.05.2017 | Pavlo Shevchenko
Handling user inputs | Front-end | Implementation | 10.05.2017 | 15.05.2017 | Ali Hashaam
AQP(architecture/components). | All | Research | 11.05.2017 | 14.05.2017 | Guzel Mussilova, Ali Raza
Implementation of Sketches in JAVA | All | Research | 14.05.2017 | 14.05.2017 | Ali Raza
Team meeting | All | Meeting | 15.05.2017 |  | Guzel Mussilova
MS-II. Concepts | All | Presentation | 15.05.2017 | 22.05.2017 | Guzel Mussilova, Ali Raza
Meeting with Supervisor | All | Meeting | 17.05.2017 |  | Gabriel Campero
HyperlogLog(working principle) | All | Research | 18.05.2017 | 22.05.2017 | Guzel Mussilova, Ali Raza
Integration DP&JN | All | Implementation | 18.05.2017 | 22.05.2017 | Ali Hashaam, Pavlo Shevchenko
Processing JSONHandler Function | Front-end | Implementation | 18.05.2017 | 25.05.2017 | Ali Hashaam
Query Manager | Back-end | Implementation | 20.05.2017 | 22.05.2017 | Pavlo Shevchenko
Team meeting | All | Meeting | 22.05.2017 |  | Guzel Mussilova
MS-II. Concepts | All | Presentation | 23.05.2017 |  | Guzel Mussilova, Ali Raza
Meeting with Supervisor | All | Meeting | 24.05.2017 |  | Gabriel Campero
Introduction(part.) | All | Scientific Writing | 24.05.2017 |  | Guzel Mussilova
Visualization | All | Implementation | 25.05.17 |  | Ali Hashaam
Team meeting | All | Meeting | 29.05.2017 |  | Guzel Mussilova
Meeting with Supervisor | All | Meeting | 31.05.2017 |  | Gabriel Campero
Team meeting | All | Meeting | 05.06.2017 |  | Guzel Mussilova
Meeting with Supervisor | All | Meeting | 07.06.2017 |  | Gabriel Campero
Team meeting | All | Meeting | 12.06.2017 |  | Guzel Mussilova
MS-III. Implementation | All | Presentation |  | 12.06.2017
MS-III. Implementation | All | Presentation | 13.06.2017
Meeting with Supervisor | All | Meeting | 14.06.2017 |  | Gabriel Campero
Team meeting | All | Meeting | 19.06.2017 |  | Guzel Mussilova
Meeting with Supervisor | All | Meeting | 21.06.2017 |  | Gabriel Campero
Team meeting | All | Meeting | 26.06.2017 |  | Guzel Mussilova
Meeting with Supervisor | All | Meeting | 28.06.2017 |  | Gabriel Campero
Team meeting | All | Meeting | 03.07.2017 |  | Guzel Mussilova
MS-IV. Final | All | Presentation |  | 03.07.2017
MS-IV. Final | All | Presentation | 04.07.2017